# FEASIBILITY ANALYSIS

TIET Campus Social Platform

Technical, Economic, Operational and Schedule Feasibility

with Team Workload Allocation

Prepared for Faculty Evaluation

Team Members: Ananya | Hitesh | Bhavya | Pratham

UCS503 - Software Engineering | August 2026

Decision: Proceed with a controlled MVP using only free tiers, open-source software, existing laptops and available internet.

# 1. Executive Feasibility Decision

The TIET Campus Social Platform is feasible as a semester MVP, but the complete production-scale vision is not feasible for four students in one semester. The recommended first release includes verified sign-in, profiles, posts and reels, a basic feed, communities, reporting, moderation status, and an administrator review screen. Messaging, Stories, local machine-learning moderation, read replicas, and full resilience demonstrations should be attempted only after the MVP passes its quality gates.

| Dimension | Decision | Reason |
| --- | --- | --- |
| Technical | Feasible with controlled scope | The stack is widely supported, modular and locally runnable. |
| Economic | Feasible at Rs. 0 direct cost | Only free tiers, open-source tools and existing equipment are used. |
| Operational | Feasible for a controlled pilot | Verified identity and moderation match campus needs. |
| Schedule | MVP feasible; full scope is not | A 12-week staged plan prevents optional features from blocking submission. |
| Team | Feasible with clear ownership | Pratham leads major coding and every member owns measurable outputs. |

## Evaluation Criteria

- Can the platform solve campus-specific identity, governance and moderation needs better than a collection of unrelated applications?

- Can four students implement, integrate, test and demonstrate the MVP within one semester?

- Can the team operate at Rs. 0 direct expenditure using free tiers and local open-source services?

- Can private content and institutional identities be protected during the classroom pilot?

# 2. Existing Solutions and Comparative Value

Existing platforms are more mature in their specialist areas, but no single alternative provides the proposed combination of verified @thapar.edu membership, campus-only discovery, institution-controlled moderation, communities, reels, messaging and academic ownership of the system design. The project is therefore justified as a campus-specific pilot and learning platform, not as an attempt to outperform global products at global scale.

| Alternative | Where it is stronger | Gap for TIET use | Proposed value |
| --- | --- | --- | --- |
| Instagram / TikTok | Highly polished reels and discovery | Public network, advertising and limited institutional control | Verified campus-only access and local governance |
| WhatsApp | Mature direct and group messaging | Weak content discovery; phone-number-centred identity | Social discovery plus campus messaging in one system |
| Discord / Teams | Strong channels, groups and collaboration | Not designed around reels, campus feeds and explainable ranking | Student-social experience with controlled communities |
| Combination of existing apps | Immediate availability and no development | Fragmented identity, privacy, moderation and administration | One policy, audit trail and consistent campus experience |

## Organizational Benefit

- Verified institutional access reduces impersonation and unauthorized participation.

- One reporting, moderation, appeal and audit workflow improves accountability.

- Campus content and communities become discoverable through one consistent interface.

- The institute gains a reusable academic platform for software engineering, databases, security and usability evaluation.

- The expected benefit is engagement, governance, safety and learning rather than direct financial profit.

# 3. Technical Feasibility

Technical feasibility is positive for the MVP because the architecture uses common technologies and a feature-based modular monolith rather than premature microservices. Next.js provides the mobile-first interface, Express provides one controlled business API, PostgreSQL is the source of truth, and workers handle selected asynchronous tasks. Kafka, replicas and advanced local machine-learning services can be added after the synchronous core is stable.

| Area | Technology | Assessment | Justification |
| --- | --- | --- | --- |
| Frontend | Next.js, React, TypeScript, Tailwind CSS | Feasible | Strong ecosystem and mobile-first PWA support |
| Backend | Node.js, Express, TypeScript | Feasible | One modular API simplifies authorization and transactions |
| Identity and data | Supabase Auth, PostgreSQL, Storage, Realtime | Feasible | Free/local options support RLS, private storage and signed uploads |
| Events and cache | Kafka and Valkey | Conditional | Introduce after core flows; local containers consume memory and integration time |
| Moderation | Rules, mock provider, optional local models | MVP feasible | Deterministic checks and human review are realistic |
| Testing | Vitest, Supertest, Playwright, k6 | Feasible | All selected tools are free and can be introduced progressively |

## Technical Risks and Controls

- Scope risk: complete the core social and moderation flow before Messaging, Stories, replicas and advanced ranking.

- Integration risk: maintain OpenAPI, event schemas, migrations and shared TypeScript contracts before parallel implementation.

- Privacy risk: enforce authentication, role checks, PostgreSQL Row Level Security, private storage and authorization tests.

- Media risk: limit upload size and duration, quarantine files and begin with a deterministic moderation mock.

- Knowledge concentration risk: Pratham reviews high-risk integration, while each subsystem retains documentation and a secondary reviewer.

# 4. Operational Feasibility

The system is operationally suitable for a controlled TIET demonstration because onboarding is restricted to institutional accounts, visibility can remain campus-only, and administrators receive explicit review and audit workflows. A real deployment would still require formal policy approval, assigned moderators, support ownership, incident handling, backups and privacy review.

## Pilot Acceptance Conditions

- Verify that external email addresses cannot complete onboarding.

- Demonstrate that unrelated or blocked users cannot retrieve private content.

- Keep flagged media private until an administrator records a decision.

- Provide reproducible seed data, demo accounts and a documented start-up procedure.

- Present the classroom deployment as a pilot, not an unmeasured production service.

# 5. Economic Feasibility - Strict Zero-Cost Baseline

The project is economically feasible for development and classroom demonstration at Rs. 0 direct expenditure. Every mandatory component is open-source, offered through a free tier, or already owned by the team. No paid domain, hosting plan, software licence, cloud compute, database plan, moderation API or new hardware is included.

| Resource | Selected option | Direct cost | Control |
| --- | --- | --- | --- |
| Development and source control | VS Code, Git, GitHub, Node.js, pnpm | Rs. 0 | Free/open-source or educational access |
| Frontend and backend | Next.js, React, Tailwind CSS, Express, TypeScript | Rs. 0 | Free/open-source |
| Identity, database, storage, realtime | Supabase free tier or self-hosted local stack | Rs. 0 | Monitor and remain within quotas |
| Events, cache, observability | Kafka, Valkey, Prometheus, Grafana | Rs. 0 | Run locally in containers |
| Testing and media tools | Vitest, Playwright, k6, ClamAV, FFmpeg | Rs. 0 | Free/open-source |
| Moderation | Mock provider and optional local open-source models | Rs. 0 | No paid API |
| Hardware and network | Existing laptops and available internet | Rs. 0 | No new purchase |
| Total direct expenditure |  | Rs. 0 | Strict semester baseline |

## Economic Comparison

Existing applications require no development if the only objective is messaging or posting. This project becomes economically reasonable as an academic pilot because it adds TIET-specific verification, one moderation process, local governance, auditable administration and a reusable codebase without direct expenditure. The Rs. 0 conclusion applies only to development and classroom demonstration; public production deployment would require a separate operating-cost assessment.

## Free-Tier Controls

- Paid services, APIs, domains and hardware are outside the approved semester baseline.

- Hitesh maintains the zero-cost resource register and checks quotas before each milestone.

- When a limit is reached, reduce demo data, use local containers or switch to a mock adapter instead of purchasing capacity.

- Cap media size, demo accounts, retention and load tests to fit free storage and compute.

# 6. Schedule Feasibility

| Period | Phase | Exit deliverable | Primary owners |
| --- | --- | --- | --- |
| Weeks 1-2 | Foundation | Scaffold, wireframes, ERD, migrations, authentication and CI | Pratham, Bhavya, Ananya |
| Weeks 3-5 | Core social MVP | Profiles, posts/reels, media, comments, reactions and communities | Pratham, Bhavya |
| Weeks 6-7 | Feed and moderation | Basic ranking, reports, moderation states and admin queue | Pratham, Ananya, Hitesh |
| Weeks 8-9 | Integration and quality | API integration, RLS, E2E, accessibility and defect fixing | All members |
| Weeks 10-11 | Optional extensions | Kafka/Valkey demo; messaging or stories only if MVP is stable | Pratham with team support |
| Week 12 | Submission | Smoke test, rehearsal, final report, presentation and backup | All members |

# 7. Workload Allocation Among Four Members

Responsibilities are assigned according to current strengths while preserving a measurable contribution from every member. Pratham receives the largest coding and integration responsibility; Bhavya owns UI/UX and frontend delivery; Ananya owns database design and data integrity; and Hitesh owns economic feasibility, QA coordination and submission documentation.

| Member | Primary role | Share | Owned outputs |
| --- | --- | --- | --- |
| Pratham | Architecture and major coding lead | 40% | Backend foundation, authentication, business modules, API contracts, workers, integration and code review |
| Bhavya | UI/UX and frontend lead | 25% | Wireframes, design system, responsive Next.js screens, accessibility and frontend tests |
| Ananya | Database design and integrity owner | 18% | ERD, schema, migrations, constraints, seed data, RLS and query verification |
| Hitesh | Economic analysis, QA and documentation owner | 17% | Zero-cost register, feasibility evidence, test cases, manual QA, demo checklist and final documents |

## Pratham - Architecture and Major Coding Lead

- Finalize modular boundaries, repository structure, coding standards, shared contracts and integration strategy.

- Implement the Express foundation, authentication, authorization, validation, error handling and major social-content services.

- Implement the outbox and selected Kafka/worker flows after the synchronous MVP is stable.

- Integrate frontend, database, storage and realtime paths; resolve complex defects and review high-risk changes.

- Evidence: running API, reviewed architecture, integrated MVP, passing critical tests and technical demonstration.

## Bhavya - UI/UX and Frontend Lead

- Produce user flows, wireframes, responsive layouts and a consistent TIET-inspired design system.

- Implement Next.js screens for onboarding, feed, creation, profiles, communities, moderation states and admin review.

- Connect approved APIs and verify loading, empty, error, mobile and accessibility states.

- Evidence: approved wireframes, reusable components, responsive primary flows and frontend tests.

## Ananya - Database Design and Data Integrity Owner

- Maintain the ERD and map requirements to tables, keys, relationships, constraints, indexes and retention rules.

- Write schema migrations, seed data and Row Level Security policies with Pratham review.

- Test duplicate prevention, foreign keys, soft deletion, permissions and representative queries.

- Evidence: versioned ERD, reproducible migrations, seeded data, RLS results and data dictionary.

## Hitesh - Economic Feasibility, QA and Documentation Owner

- Maintain the zero-cost resource register, monitor free-tier limits and document institutional value.

- Convert requirements into acceptance cases and coordinate manual testing, defects and regression checks.

- Support API tests and test-data preparation under Pratham and Ananya review.

- Evidence: feasibility report, resource register, test results, defect summary, user guide and submission checklist.

# 8. Collaboration and Review Matrix

| Work product | Owner | Reviewer | Completion rule |
| --- | --- | --- | --- |
| Architecture and API | Pratham | Bhavya | Contracts approved before UI integration |
| UI/UX and frontend | Bhavya | Pratham | Responsive and accessible primary flows |
| Database and RLS | Ananya | Pratham | Migration review plus authorization tests |
| Cost and feasibility | Hitesh | Pratham | Rs. 0 direct cost and verified free-tier assumptions |
| Testing and demo | Hitesh | All members | Critical journeys pass in a clean environment |
| Final documentation | Hitesh | All members | Each owner signs off their section |

## Weekly Working Method

- Monday: agree weekly scope and acceptance criteria; avoid unplanned features.

- Mid-week: integrate small changes and review contracts, migrations and UI states.

- Friday: demonstrate completed work, update risks and free-tier usage, and select defects.

- Before each milestone: run a clean setup, critical tests, seeded demo and backup check.

# 9. Final Recommendation

The team should proceed with the TIET Campus Social Platform as a staged academic project. It is technically and economically feasible when the MVP is protected and the documented free-tier/open-source baseline is followed, resulting in Rs. 0 direct project expenditure. Existing solutions remain superior for mass-market scale and specialist features, but the proposed platform provides stronger value for verified campus identity, local governance, integrated moderation and software-engineering learning.

Approval should be conditional on three controls: finish verified authentication and the core social/moderation flow before optional features; require tests for authorization and private data; and defer any feature that threatens the week-12 demonstration. Under these conditions, the allocation is realistic and every member has a clear, assessable contribution.

## Team Acknowledgement

| Member | Responsibility accepted | Signature |
| --- | --- | --- |
| Ananya | Database design and data integrity | ________________ |
| Hitesh | Economic feasibility, QA and documentation | ________________ |
| Bhavya | UI/UX and frontend | ________________ |
| Pratham | Architecture and major coding | ________________ |